## Sheet1
Capstone Update (rstreeter@hrsa.gov) | 2018-07-27
Objective: Pilot a set of tools to help answer the “where”
•Children’s Hospitals Graduate Medical Education (CHGME) program
•CHGME provides funding to support pediatric residencies
Capstone questions:
•In what counties are AY 2016-2017 CHGME graduates practicing?
•What are the characteristics of the populations in these counties?
Data sources
•NPIs from HRSA program data
•Provider location data from NPPES
•County level data from HRSA' s Area Health Resources Files
Tasks
•Clean CHGME NPIs |  | Complete
•Obtain locations for all CHGME NPIs |  | Complete
•Clean and format zip codes |  | Complete
•Use zip code to identify practice locations |  | Complete for approximately 85 percent of graduates
• Assign FIPS codes (state and county) to each location |  | Complete
•Tabulate provider counts by FIPS code |  | Complete
•Create AHRF sub dataset |  | In process
•Link to AHRF data |  | Pending creation of AHRF dataset with selected variables)
• Preliminary EDA of AHRF data |  | Complete
•Estimate current provider ratios for physicians, dentists
•Create selected cross tabulations
•Compare shortage areas, provider ratios, median age, median income, and rural status
• Examine characteristics of counties with higher proportion of CHGME graduates
• Prepare maps
• Summarize findings
• Plan next steps
•Consider more granular analysis
•Develop analysis using contiguous geographies
Challenges
• R packages for specialized functions | Fix: Google!
• Massive datasets | Fix: SAS :-(
• Missing data | Fix: ?? [Need to understand the source of the missingness]
• Zipcodes and counties overlap | Fix: ?? [May not be issue, if characteristics of adjacent county are similar)
Where are we not?
Fread (data.tables)
Unsupervised - clustering, remove shortage area as outcomes
what are characteristics of each cluster
Logistic regression - important in determining partial or whole shortage
Rates
Decision tree
Diversity indices
Problems with shortage areas - they don't measure what folks think they measure
sparse pop, rational service areas, pop and facility shortages